## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | SJ; 10/7/2019
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | SJ; 10/7/2019
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | SJ; 10/7/2019
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | SJ; 10/7/2019
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | SJ; 10/7/2019
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | SJ; 10/7/2019
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | SJ; 10/7/2019
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | SJ; 10/7/2019
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | SJ; 10/7/2019
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | SJ; 10/7/2019
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | SJ; 10/7/2019
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | SJ; 10/7/2019
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | SJ; 10/7/2019
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | SJ; 10/7/2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | SJ; 10/7/2019
As a player I want the red pieces to move first so that I can continue playing against an opponent | **Given** that I am a signed in user, **when** the game starts, **then** the red piece user will move first |  |  | Pass | SJ; 11/3/2019
| **Given** that I am the red piece user, **when** I try to move my red piece, **then** the first move must be a simple move |  |  | Pass | SJ; 11/3/2019
| **Given** that I am the red piece user, **when** I complete my move, **then** I am unable to move until the white piece user completes their turn |  |  | Pass | SJ; 11/3/2019
| **Given** that I am the red piece user, **when** I complete my move, **then** the text box should update saying that it is the white piece user's turn |  |  | Pass | SJ; 11/3/2019
| **Given** that I am the red piece user, **when** I am making my move, **then** I must move a piece before I click "Submit Move" |  |  | Pass | SJ; 11/3/2019
As a player I want to be able to move my piece to a vacant dark square by moving one spot diagonally so that I only make legal moves | **Given** it is my turn, **when** I drag and drop a piece to a an empty diagonal dark square, **then** the board and my opponent’s view should update accordingly |  |  | Pass | SJ; 11/3/2019
| **Given** it is not my turn, **when** I try to drag and drop to make a move, **then** I should not be allowed to change the board |  |  | Pass | SJ; 11/3/2019
| **Given** it is my turn, **when** I complete my move, **then** the active color changes to my opponents color |  |  | Pass | SJ; 11/3/2019
| **Given** i have a jump move available, **when** I try to make a single move, **then** I should not be allowed to make a single move, but forced to do the jump move |  |  | Pass | SJ; 11/3/2019
| **Given** it is my turn, **when** I pick up a piece, **then** the legal squares should be highlighted |  |  | Pass | SJ; 11/3/2019
As a player I want to be able to capture the opponent’s piece by jumping over it diagonally and landing on a vacant dark square so that I can progress the game towards victory | **Given** I'm playing a game, **when** I want to capture a single piece **then** I can perform a single jump move. |  |  | Pass | SJ; 11/3/2019
| **Given** I'm making a single jump move, **when** I place my piece, **then** the game should verify if the space the piece is landing is valid (adjacent empty black square). |  |  | Pass | SJ; 11/3/2019
| **Given** that I complete a jump move, **when** I place my piece into a vacant, valid spot, **then** the opponent's piece should be visibly and physically removed from the board after submitting |  |  | Pass | SJ; 11/3/2019
As a player I want to force my opponent to make a jump move if available so that I can advance my strategy | **Given** that I can hop over a single enemy piece, **when** it is possible to perform another jump, **then** perform another jump |  |  | Pass | SJ; 11/3/2019
| **Given** that I have hopped over multiple enemy pieces, **when** I finish my turn by landing in a valid empty dark space, **then** the enemy pieces that were hopped over should be removed from the board |  |  | Pass | SJ; 11/3/2019
| **Given** that I have performed a multiple jump move, **when** I finish my turn, **then** the next player should be able to make a move |  |  | Pass | SJ; 11/3/2019
| **Given** that it is not my turn, **when** I attempt to move a piece, **then** I should not be able to change the board state until it is my turn |  |  | Pass | SJ; 11/3/2019
| **Given** that I move a piece doing a multiple jump move, **when** I try to click the submit button, **then** my move should be validated posting an error message if invalid |  |  | Pass | SJ; 11/3/2019
As a player I want to be able to promote my pieces to a King so that I can move backwards | **Given** that I have made a move, **when** my piece reaches the other end of the board, **then** my piece should promote to a king piece and visibly have a piece placed on top of it |  |  | Pass | SJ; 11/3/2019
| **Given** that I have a king piece, **when** I make a move, **then** I should be able to move backwards or forwards diagonally |  |  | Pass | SJ; 11/3/2019
| **Given** that I am making a jump move, **when** I jump using the king piece, **then** I should be able to capture opposing pieces in forward or backward directions |  |  | Pass | sJ; 11/4/2019
| **Given** that I am making a jump move, **when** I multi jump using the king piece, **then** I should be able to take a piece with a combination of forward and backward jumps |  |  | Pass | SJ; 11/4/2019
As a player I want to force my opponent to make a jump move if available so that I can advance my strategy | **Given** that it is my turn, **when** I am trying to move a piece, **then** I must complete a move in order to abide by the game rules |  |  | Pass | SJ; 11/3/2019
| **Given** it is my turn, **when** there is an available jump move, **then** I must perform a jump |  |  | Pass | SJ; 11/4/2019
| **Given** that it is my turn, **when** there is no available jump move, **then** I am not forced to perform a jump move |  |  | Pass | SJ; 11/3/2019
| **Given** it is my turn, **when** there are multiple different single jump moves available, **then** I should be able to pick whichever piece a complete a jump move |  |  | Pass | SJ; 11/4/2019
| **Given** it is my turn, **when** there are multiple types of moves available including a jump move, **then** I must make the jump move |  |  | Pass | SJ; 11/3/2019
As a player I want to win the game when my opponent loses all their pieces, can’t make a move, or resigns, so I enjoy the game | **Given** that there are no more opposing pieces, **when** I have eliminated the opponent's last piece, **then** I should have been notified that I won the game |  |  | Pass | SJ; 11/4/2019
| **Given** that I have no more pieces, **when** the opponent has eliminated my last piece, **then** I should have been notified with a message that I lost the game |  |  | Pass | SJ; 11/4/2019
| **Given** that a user has no more pieces, **when** both users have received their game status notifications, **then** the game board should no longer be able to interact with |  |  | Pass | SJ; 11/4/2019
As a player I want to be able to resign at any time so that I can quit without playing the rest of the game | **Given** I am in a game, **when** I want to leave before the game ends, **then** I should see a means to resign |  |  | Pass | SJ; 11/3/2019
| **Given** I am in a game, **when** I resign, **then** I should lose the game |  |  | Pass | SJ; 11/4/2019
| **Given** I make a valid move, **when** I drag a piece, **then** the resign button should be not interactable |  |  | Pass | SJ; 11/3/2019
As a player, I want to be able to sign-out, so that I can leave the application | **Given** that I am signed in, **When** I view any page, **Then** I must see a means to sign out. |  |  | Pass | sJ; 11/3/2019
| **Given** I am not signed out, **When** I sign out, **Then** I will be redirected to the home page, which shows the number of players online. |  |  | Pass | SJ; 11/3/2019
| **Given** I am not signed out, **When** I sign out, **Then** the system should remove my player from the list of online players. |  |  | Pass | SJ; 11/3/2019
As a player with an account, I want to be presented an interface so I can access the view replay functionality | **Given** that I have finished a game, **when** the game has determined a winner, **then** I want to see a means to replay a game
**Given** that I am in a game, **when** the game is not finished, **then** I should not see a means to replay a game
**Given** that I have finished a game, **when** the other player has left, **then** I should still be able to replay the game
**Given** that I am in the replay mode, **when** I want to exit back to home page, **then** I should see a means to exit
As a player I want to be able to look through the game progression one move at a time and be able to traverse turns forward and backwards so that I can best analyze the game | **Given** that the game is over, **when** the player enters the replay mode, **then** the player should see a means to traverse back and forward turns
**Given** that the player is in replay mode, **when** the player wants to move forward a turn, **then** the board should update to the next most recent move
**Given** that the player is in replay mode, **when** the player wants to move back a turn, **then** the board should update to the next previous turn
**Given** that the player is in replay mode, **when** a player attempts to move forward or backwards a turn and there were no more turns beyond that point, **then** a message should indicate that there were no turns forward or backwards from the current turn
**Given** that a player is in replay mode, **When** the player hits exit, **then** the player should be redirected home
As the player I would like to be able to play against an AI so that I will always have an opponent | **Given** that I am a signed in user, **when** I am on the home page, **then** I should see a means to play against an AI player
**Given** that I start a game against an AI, **when** the game starts, **then** both the AI and the player should follow the same rules of checkers
**Given** that I start a game against an AI, **when** the game starts, **then** I should be the red player
**Given** that I am in a game against an AI, **when** it is the AI's turn, **then** the AI should perform a valid move and submit their turn
As the player I would like the AI to follow the same rules and movement as the player so that the game can be played fairly | **Given** that it is the AI's turn, **when** they perform a move, **then** the move must abide to the rules of checkers
**Given** that it is the AI's turn, **when** they perform a move and there is an available jump, **then** the move must be a jump
**Given** that it is the AI's turn, **when** they perform a jump and there are multiple jumps, **then** then the AI must perform all the available jumps